## Gantt Chart
|  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
| Project Network |  | 2016-12-26 | 2016-12-27 | 2016-12-28 | 2016-12-29 | 2016-12-30 | 2016-12-31 | 2017-01-01 | 2017-01-02 | 2017-01-03 | 2017-01-04 | 2017-01-05 | 2017-01-06 | 2017-01-07 | 2017-01-08 | 2017-01-09 | 2017-01-10 | 2017-01-11 | 2017-01-12 | 2017-01-13 | 2017-01-14 | 2017-01-15 | 2017-01-16
Responsibility
1 | StoreViz internal meeting |  | 2016-12-26: meetings and discussions(); 2016-12-27: meetings and discussions(); 2016-12-28: explain flow and functionalities of SV to all team specially new team members
2 | Website Theme for Storeviz | Searching theme, choose the best one , implement it | 2016-12-29: Faiza Shaikh & Shahnawaz Ali
| Customer Profile |  | 2016-12-30: F Shaikh; 2016-12-31: F Shaikh; 2017-01-02: F Shaikh
3 | Customer Name
4 | Email Address
5 | Contact Details
6 | Upload Logo
7 | Customer code
8 | Demo Sign Up
Data Management
9 | Master Data management Channel/StoreCode/StoreName/Region/landmark/Locality/Sublocality/Lat-Long. |  | 2017-01-03: F Shaikh; 2017-01-04: F Shaikh; 2017-01-05: F Shaikh
10 | Upoload Product Details -Category/Sub-Category/Brands/Skus |  | 2017-01-03: Salman Memon; 2017-01-04: Salman Memon; 2017-01-05: Salman Memon
11 | Create Staff field -Supervisior/Merchandisor/Auditors |  | 2017-01-03: Shahnawaz; 2017-01-04: Shahnawaz; 2017-01-05: Shahnawaz
Merchandising Task
12 | Module s -OSA/SOS/Visibility-Proposition/Planogram/Images |  | 2017-01-07: Shahnawaz , F Shaikh , Salman; 2017-01-10: Shahnawaz , F Shaikh , Salman
13 | Module Configuration |  | 2017-01-13: Shahnawaz , F Shaikh , Salman
Handing over to you for further testing (on 16th Janaury)